## Sheet1
For More Information Contact Software Analysis Corporation
Implement New Technology in a Mid to Large Size Firm
Create a Project Team
One Project Manager
Each Department must be represented
One Attorney from Each Department
One Paralegal or Assistant from Each Department
At least one Billing and Accounting Person
At least one File Room / Runner
Create a Project Plan
Spell out Responsibilities
Identify Milestones
Identify Deliverables
Roll out in Phases
Create a Timeline
Take into account busy times such as month/year end and trials
Publish the Plan
Obtain Signatures from Project Team
Sign the Project Plan
Sign off on Timeline
Sign off on Deliverables and Milestones
Monitor the Plan
Compare projected to Actual
Modify the plan as needed
Publish the Plan Revisions
Needs Analysis from the ground up
Start with Reports
Create a Data Dictionary
Do the Data Fields mean the same thing on every report?
Find out who uses the report
What Information does the report give them
How do they use the information
What information doesn't the report give them that they need
Observe what steps are taken to produce the report
Use this information to start building your Needs Analysis
Observe how each department works
Interview people in the department
What are their biggest challenges?
What is their wish list?
What does not work?
What would they change?
Invite additional feedback if they missed something
Create a Needs Analysis Worksheet
Determine type(s) of Software needed
Determine type(s) of Hardware needed
List Features Needed
Rank Feature Importance
Perform a Search
Arrange for Demos
In advance, provide them with your list of "must have" items
In advance, provide them with copies of your "must have" reports
Arrange for 3 people in your firm to see the Demos
While watching the Demo, check of your features that match
Add features you see that you like to your Features List
Narrow down your search to top 3 packages
Arrange for second demo and include decision makers
Decide on a Package(s)
Ask for a test migration
If possible, roll out by department
Outline responsibilities
Outline timeline and deliverables
Balance Data
Provide for training
Catalog problems
Make sure all problems are resolved
Arrange for follow up training in a month
Project Wrap Up
Meet with users for feed back
Compare Features List to what is being used
Arrange for additional training if necessary
Close the project plan with a sign off
Discuss next phase options
Note on A7: Gerri Lynn Martin: Preferably not the attorney's paralegal
Note on A28: Gerri Lynn Martin: Fancy talk for define what each field on the report means
Note on A34: Gerri Lynn Martin: Often it is exported to Excel and modified or reformatted from there
Note on A37: Gerri Lynn Martin: Do not give them the questions in advance or you will get scripted, "party-line" answers.
Note on A47: Gerri Lynn Martin: I use a scale of must have, would be nice, not important
Note on A66: Gerri Lynn Martin: People will forget most of what they learned People will complain about the program if they don't know how to use it properly